## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-261-05-d Big Development
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase.
| Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. | Pass | CJH; 10/19/22
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. | Pass | CJH; 10/19/22
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. | Fail | CJH; 10/19/22 - when there is no product available, no message is displayed. Ex: http://localhost:4200/product-page/67 entered in nav bar
| Given that I am on a products page when there are products in the inventory then I see a means to add each product to my shopping cart. | Pass | CJH; 10/19/22
As a Developer I want to maintain the user data in files so that I can preserve user information and ensure users see the shop in the same state which they left it.
| Given I have signed in with an account before when I enter my username then the system recognizes my username and logs me into my account | Pass | MV; 10/19/22
| Given I have previously added items to my cart when I sign in to my account the system will maintain the items I had in my cart | Pass | MV; 10/19/22
| Given I am an admin when I choose to remove a user, the user is removed from the database. | Pass | MV; 10/19/22
| Given I am a user who has signed in, when I open my profile I am able to edit all of the information besides my username. | Pass | MV; 10/19/22
| Given I am an admin who is logged in, when I try to delete the admin account an error occurs. | Pass | MV; 10/19/22; there is no pop-up or text indicating an error occurs, but the admin cannot be deleted
As an admin I want to access to user accounts so that I can help users manage their account.
| GIVEN I am an administrator in the admin dashboard when create a user then a user gets created | Pass | MV; 10/19/22
| GIVEN I am an administrator in the admin dashboard when I update a user then the user gets updated | Pass | MV; 10/19/22
| GIVEN I am an administrator in the admin dashboard when I delete a user then the user gets deleted | Pass | MV; 10/19/22
| GIVEN I am an administrator in the admin dashboard when I get a user then the users information gets displayed | Pass | MV; 10/19/22
| GIVEN I am an administrator in the admin dashboard when I get a list of users then all the users get displayed | Pass | MV; 10/19/22
As a customer I want to create an account so that I can save my information.
| Given I am a new customer, when I create an account, my username cannot overwrite an existing customers data. | Pass | MV; 10/19/22
| Given I am a new customer, when I create an account, I am able to use that account to save information. | Pass | MV; 10/19/22
As a customer I want to view my cart so that I can verify what I want to purchase
| Given I am signed in as a customer with items in my cart when I navigate to the cart then the system will Display all the items in my cart. | Pass | AL; 10/19/2022.
| Given I am not signed in as a customer, when I navigate to the cart, then the system will notify me that I must sign in to view the cart | Pass | AL; 10/19/2022.
| Given I am signed in as an admin, when I attempt to navigate to the cart, then the system will notify me that an admin is unable to view the cart | Pass | AL; 10/19/2022.
| Given I am signed in as a customer and have items in my cart, when I navigate to the cart, the system will show me how much all items in my cart will cost in total. | Pass | AL; 10/19/2022.
As a customer I want to add my selected product to my shopping cart so I can make a list of items I want to purchase.
| Given I have chosen a selected product and the product has available stock, when I press a add to cart button then I expect the item to be added to my cart. | Pass | AL; 10/19/2022.
| Given a certain product is within my cart, if I choose to add additional units to my cart, then the system will update the quantity in the cart | Pass | AL; 10/19/2022 Test passed. I found that when I press add to my cart a second time on a product I already added, it updates the quantity. This is fine, except that perhaps the 'add to my cart' button should go away once it is added.
As a customer I want to be able to remove a selected product from my shopping cart so that I can only have the items I want in my cart.
| Given I am a customer viewing my cart when I press a trash button then that product will no longer be in my cart | Pass | AL; 10/19/2022.
As a user I want to view an order so I can verify my order's details and check its current status
| Given I am logged in as a customer and an order was placed by me, when I navigate to an order then the system will show me the address, payment info, and items I chose to order | Pass | AL; 10/19/2022.
| Given I am logged in as a customer when I attempt to view an order that was not placed by me, the system will notify me that I'm not able to view that order. | Pass | AL; 10/19/2022.
| Given I am not logged in, when I attempt to view an order, then the system will notify me I must sign in to view an order | Pass | AL; 10/19/2022.
| Given I am an admin, when I attempt to view any order, then the system will show me all order details | Pass | AL; 10/19/2022.
As a user I want to be able to place my order so that I can complete the checkout process.
| Given I am signed in as a customer and reviewing a drafted order, when I submit my order, the system will notify me the order has been received. | Pass | AL; 10/19/2022.
| Given I am signed in as a customer and reviewing a drafted order, when I submit my order, the system will add the submitted order to my profile's order history. | Pass | AL; 10/19/2022.
As a user I want to select a product so that I can view its details and decide if I want to purchase it.
| Given I am a customer, when I select a product from the home page, then I should be taken to that product's page. | Pass | CJH; 10/19/22
As a user I want to view a product so that I can see its details and add it to my cart.
| Given I am a user who is signed in, when I am on a product's page, then I should see its details and be able to add it to my cart. | Pass | CJH; 10/19/22
| Given I am a user who is not signed in, when I am on a product's page, then I should see its details, but cannot add it to my cart, and should be prompted to sign in or create an account. | Pass | CJH; 10/19/22
As an admin I want to mark orders as fulfilled so that I can track which orders I still need to complete.
| Given I am logged in as an admin when I mark an order as fulfilled then the order will be marked as fulfilled. | Pass | RC; 10/19/22;
As a Owner I want to be able to cancel any orders that I cannot fulfill so that my customers continue to buy from me.
| Given I am an owner reviewing placed orders when I press a cancel button on an order then the system will cancel the order for the specified user | Pass | RC; 10/19/22;
As an admin I want to update my inventory, such that product information is reflected properly.
| Given I am logged in as admin when I submit a new inventory then the system overwrites the current inventory to reflect the changes. | Pass | RC; 10/19/22;
| Given I am admin on when I select a product to update in the inventory then the system brings me to a page where I can see and edit the details of the product | Pass | RC; 10/19/22; test passed but the UI needs to be fixed. The button used to submit changes says "Add new product" instead of "update" or "save"
| Given I am admin when I update a product and save It then all my customers currently on the system will have access to what I have changed | Pass | RC; 10/19/22;
As an admin I want to be able to create and add an item to the store's inventory so that it is available for purchase.
| Given I am logged in as an admin when I add an item to the store's inventory then I expect that the store page is updated with the correct item. | Pass | RC; 10/19/22; The error message that is displayed should be more specific. Entering a duplicate id results in a "server error" message and you should display a message that says "no duplicate id's"
As a Developer I want to have a reusable component so that I can quickly display the main details of a product
| Given I am looking to view falcons products when I open the Falcon e-store to see their products then I will see similar styled listings of all the products | Pass | CJH; 10/19/22
| Given I am on the e-store when I go to a page looking to see available products then I will see a list of Product Components displaying each individual product | Pass | CJH; 10/19/22
As an admin I want to manage my products so that my customers can buy the right products.
| Given I am logged in as an admin when I go on the website then I should see an option to handle administrative actions | Pass | CJH; 10/19/22
| Given I am on an administration page when I select a product then I will be able to see details of the current product and edit those details | Pass | CJH; 10/19/22
| Given I am on an administration page when select an option to create a new product then I am taken to a page where I can create a brand new product | Pass | CJH; 10/19/22
As a Developer I want to have navigation in the e-store so that users and administrators can access the pages that they need.
| Given the website is partially built when a user enters from any page then they should easily be able to see a way to navigate around the website | Pass | CJH; 10/19/22
| Given when I enter an address into the url then the website will give me the correct page | Pass | CJH; 10/19/22
As an admin I want to be able to create and add an item to the store's inventory so that it is available for purchase.
| Given I am admin when I am on an administration page and select an option to create a product then I expect the system to provide me with a page to specify the details of the new product | Pass | CJH; 10/19/22
| Given I have filled in the details for a new product when I select a save product option then I expect that new product to now be on the website when I go to look for it | Pass | CJH; 10/19/22
As a developer I want to have a persistence data of the orders for the store so that it is not lost and admins can make updates over time through fulfillment.
| Given that I am a customer when I place an order then the order is added to my order history | Pass | MV; 10/19/22
| Given that I am a customer when I sign in to my account a list of my past orders is accessible | Pass | MV; 10/19/22
| Given that I am a customer when I sign in I am able to access an order I placed in the past | Pass | MV; 10/19/22
| Given that I am an admin when I sign in then the system allows me to access any historical order | Pass | MV; 10/19/22
| Given that I am customer when I view an order that belongs to me then the system allows me to cancel and subsequently update that order | Pass | MV; 10/19/22
| Given that I am an admin when I view any order then the system allows me to fulfill and subsequently update that order | Pass | MV; 10/19/22
| Given that I am an admin when I view an order then the system does provide me any method to delete an order | Pass | MV; 10/19/22
As a developer I want the product detail page to display the correct product in the correct format so that the customer knows what type of product they are viewing
| Given I am a user looking for a product when I select a product to view then I will see a page tailored to the type of product I selected | Pass | CT 11/1/22
As a User I want to see products pertaining to bird accessories and sponsoring so that I can purchase or sponsor the bird or item that I like.
| Given there are products on the system when the user enters the site then they will see products of birds and accessories that are listed on the system | Pass | CT 11/1/22
As a admin I want to be able to perform CRUD operations on the products so that I can keep my stock up to date for my.
| Given a user is signed in as admin when the select an item then the system will allow them to perform CRUD operations on the selected item | Pass | CT 11/1/22
As an ornithologist I want to view a falcon dashboard so I can choose a falcon I want to submit a health report for.
Given I am an ornithologist when I login with my account then the system brings me to the falcon dashboard
Given there are falcons in the inventory, when I visit the falcon dashboard then I will be present a list of available falcons to write reports for
Given there are falcons displayed on the dashboard when I select a falcon then I am brought to the page to view falcon details with an option to add a health report
As an ornithologist I want to add health reports to a falcon so customers can receive updates on the well being of the bird
Given I am an Ornithologist when I visit a falcon on the Ornithologist dashboard then the system shows me a template to create the next health report
Given I am an ornithologist when I create a falcon's health report then the system will add the report to the falcons health history
As an ornithologist I want to update health reports so I can make corrections with accurate information
Given I am logged in as an ornithologist when I select a health report then the system shows me modifiable fields to make any changes
As a user I want to view a falcon's health report so I can stay up to date on its current well being
Given I am logged in as a user when I select a bird then the system shows me a list of a birds health reports
Given I am logged in as an user when I select a health report then the system brings me to a page to view the health report
As a developer I want to save notifications in the backend so that I can display them to users.
GIVEN the backend is running WHEN a notification is deleted, THEN it is routed correctly and saved and returns no error codes.
GIVEN the backend is running WHEN a notification is created, THEN it is routed correctly and saved and returns no error codes.
As a developer I want to be able to create notifications so I can display them to users.
GIVEN the backend is running WHEN a notification is created THEN the proper users have that notification added to their list.
As a user I want to receive notifications so that I can be informed about changes to the website that are relevant to me.
GIVEN I am a user who is signed in WHEN a notification is displayed THEN it does not get displayed again.
GIVEN I am a user with a valid account that has a backlog of notifications WHEN I log in THEN all pending notifications for me are shown.
GIVEN I am a user who is signed in WHEN a new notification is created for me THEN I see the notification.
As a user, I want to interact with every kind of product, so that I can filter them on the home page, view their pages, and add them to my cart. | NOT FULLY IMPLEMENTED
Given I am a user on the home page, when I select a product type, then I should only see that type of product.
Given I am a user, when I go to purchase a bird, I should be able to make a donation towards that bird.
Given I am a user, when I go to purchase bird accessories, I should be able to purchase however many of an accessory I would like to.
Given I am a user, when I go to purchase seminar tickets, I should be able to choose a date and time for my seminar.